## Slide 1
Quality management during the ramp-up period of new production lines
From ramp-up plan to mass production exit · Practical training
Engineering status → Structured convergence of mass production status · Knowledge No. 15.2.1
QTank
Knowledge No. 15.2.1 · New factory/new production line ramp-up
qtank.org

## Slide 2
training objectives
After completing the course, you should be able to draft the factory’s new line ramp-up plan and the war room stand-up meeting template.
Understand the nature of the ramp-up period: the gradual convergence from "functional realization" to "stable and predictable"
Master four core dimensions: equipment tooling, personnel skills, process parameters, and supply chain synchronization
Can write a "Quality Status Milestone" climbing plan and implement a rapid upgrade mechanism T0~T4
Set up a climbing war room, differentiated dashboard and "problem-countermeasure-standardization" closed loop
Avoid three major traps and officially transfer to mass production management according to six exit standards
Practical training on quality management during the ramp-up period of new production lines

## Slide 3
Course map (recommended training within 2.5 to 3.5 hours)
module | theme | duration
01 | Dilemma at the beginning + essential positioning | 25 min
02 | Four dimensions (equipment/people/parameters/supply chain) | 50 min
03 | Two tools: climbing plan + upgrade mechanism | 35 min
04 | Organization, Kanban, Knowledge Precipitation | 30 min
05 | Three major traps + mass production exit standards | 30 min
06 | Workshop: Drafting milestones for the company’s ramp-up | 30 min
Practical training on quality management during the ramp-up period of new production lines

## Slide 4
01
Quality dilemma during the ramp-up period
Why New Line always "first chaos and then cure"

## Slide 5
Opening case: 280 million new factory, complete documents but still "collapsed"
New auto parts factory: APQP / production line acceptance / PPAP all completed
Two months before mass production: customer complaints ≈ mature line × 6; scrap ≈ budget × 3; OEE ≈ 45% of design value
On-site portrait: The quality manager frequently visits customers to complain; the production director asks, "Can the goods meet the standard today?"
The root cause is not "not doing APQP", but underestimating the difficulty of management between acceptance and stable mass production.
Practical training on quality management during the ramp-up period of new production lines

## Slide 6
Engineering status vs mass production status
Project status (function implementation)
The equipment can be converted, the product can be made, and the size can be qualified Acceptance / Trial Production / PPAP focuses on "can it be made?"
Mass production status (stable and predictable)
Cpk ≥ 1.33 · The beat meets the standard · The first pass rate is stable What matters when climbing is "whether you can hold it steady every day"
Practical training on quality management during the ramp-up period of new production lines

## Slide 7
Where does the management vacuum come from?
Project Management: “Project is over” is often declared after PPAP approval
Quality department: accustomed to using "mature mass production" standards to require production lines that are still running in
Two sets of logic fighting → No one is responsible for the "convergence process" during the ramp-up period
Conclusion: Climbing must be treated as an independent stage and managed with a special mechanism, rather than a vacuum period
Practical training on quality management during the ramp-up period of new production lines

## Slide 8
02
four core dimensions
Equipment · Personnel · Parameters · Supply Chain

## Slide 9
Dimension overview: special mechanism instead of applying mature lines
① Equipment and tooling: Mainly defects during the running-in period → Parameter trend + multiple Cmk
② Personnel skills: Qualified training ≠ Muscle memory → Double mutual inspection + L1/L2/L3
③ Process parameters: design nominal value → mass production optimal value → parameter-quality matrix
④ Supply chain: sample capability ≠ batch capability → special delivery + SQE on-site
Practical training on quality management during the ramp-up period of new production lines

## Slide 10
① Equipment and tooling: stability convergence
Initial problems are mostly equipment-related defects rather than process design defects
Create an "Equipment Climbing Tracking Card": record key quality parameters + equipment status parameters daily
Example: Injection molding machine and mold temperature/injection pressure/holding pressure; machining center and vibration/tool ​​wear/coolant temperature
Trend deviation: intervene in advance before the tolerance is exceeded; it is recommended to record it every 4 hours during the climbing period
Cmk: Don’t just do the acceptance once – verify it once each in the 1st week / 2nd week / 1st month to see the trend
Practical training on quality management during the ramp-up period of new production lines

## Slide 11
② Personnel: from qualified training to muscle memory
Old employees transferred to new lines + new students: The common problem is "You still make mistakes after passing the test"
Mechanism: Two-person mutual inspection + first piece mandatory confirmation (clamping/program/tooling/first piece size)
Skill maturity level three: L1 operating under guidance → L2 independent + recognizing differences → L3 fine-tuning + teaching
Scaling goal: all employees reach at least L2; ≥30% of key positions reach L3
Practical training on quality management during the ramp-up period of new production lines

## Slide 12
③ Process parameters: feasible design → optimal for mass production
Parameter-quality matrix
Vertical axis CPP (critical process parameter) Horizontal axis CTQ (critical quality characteristic) Within the grid: strong/medium/weak + positive/negative/non-linear Quickly lock reason parameters when exception occurs
Progressive parameter adjustment principle
Only adjust one parameter at a time Amplitude ≤ design range 10% ≥50 pieces after adjustment to verify stability "Betting on luck" with multiple parameters and synchronization is prohibited
Practical training on quality management during the ramp-up period of new production lines

## Slide 13
④ Synchronous ramp-up of the supply chain
Samples are 100% qualified ≠ Consistent in batches: The gap between technician selection vs. random inspection by general workers
Issue "Special Delivery Requirements" to suppliers ≥3 months before ramping
Transition period: 100% full inspection of shipments / stricter sampling / additional inspection report for each batch
SQE on-site coaching process control, rather than just looking at the expected results
Key safety features: Our factory will conduct 100% re-inspection until the supplier’s Cpk ≥1.33 for 3 consecutive months
Practical training on quality management during the ramp-up period of new production lines

## Slide 14
03
Two core tools
Ramp-up plan + rapid upgrade mechanism

## Slide 15
Tool One: Ramp-Up Plan = Quality Status Milestones
It's not a project progress Gantt chart, but "a certain indicator reaches a certain level on a certain day"
Each station has promotion/downgrade rules: if it meets the standard, it will advance to the next stage; if it fails to meet the standard, it will trigger an extended review.
Extension review must submit: root cause analysis + corrective plan + "what else needs to be changed to meet the standards"
Philosophy: Time can be extended, but "empty extension or no action" is prohibited
Practical training on quality management during the ramp-up period of new production lines

## Slide 16
Milestone examples (can be adapted by industry)
stand | quality status target | determination
M1 | The pass rate once per day in the first month is ≥85%, and it is stable for 3 consecutive days | l/extended review
M2 | The proportion of key characteristics Cpk≥1.33 in the second month is ≥80% | l/extended review
M3 | In the third month, OEE≥design 80%, and customer complaints =0 | l/extended review
M4 | The ramp-up process will end in the fourth month and will be transferred to mass production management. | Closing review
Practical training on quality management during the ramp-up period of new production lines

## Slide 17
Tool 2: Rapid upgrade during the ramp-up period T0~T4
T0 discovery: Immediately shut down/isolate, arrive at the scene in 5 minutes
T1 1h: Initial judgment, man-machine-material method; temporary countermeasures determined
T2 4h: Verify the solidification of temporary countermeasures and resume production
T3 24h: root cause + initial long-term countermeasure plan
T4 72h: Verification of long-term countermeasures and inclusion in standard documents
Practical training on quality management during the ramp-up period of new production lines

## Slide 18
Authorization points for the upgrade mechanism
The pace is 3 to 5 times faster than the mass production period - one day of downtime may bring down the entire line of shipments
Stop or stop the line: decided by the on-site engineer, no need to wait for approval from the manager/director
Temporary countermeasures prioritize safety and isolation, and then discuss the long-term root causes.
Automatically upgrade the management level when timeout occurs at each level to avoid being "stuck on site with no one to make a decision"
Practical training on quality management during the ramp-up period of new production lines

## Slide 19
04
Organization · Kanban · Knowledge
Climbing War Room and Precipitation Closed Loop

## Slide 20
Temporary "Hill Climb War Room"
Cross-functional coworking: Production / Process / Quality / Equipment / Procurement Supply Chain (+ Key Suppliers)
Daily 30-minute hill climbing stand-up meeting, only three things:
· Yesterday’s quality indicator compliance status
· Today’s key risk items
· Issues that require upgrading cross-departmental coordination
It is prohibited to use email serialization as a substitute for on-site decision-making
Practical training on quality management during the ramp-up period of new production lines

## Slide 21
Differentiated quality signboard during ramp-up period
Granularity | Recommended indicators | use
day | First time pass rate/output achieved/abnormal shutdown/first article pass rate | Correction on the same day
week | Cpk trend/failure frequency/skill certification pass rate/incoming material qualification rate | Trend warning
moon | Scrap rate/Customer complaints/Milestones achieved | Step-up decision-making
Practical training on quality management during the ramp-up period of new production lines

## Slide 22
Red, Yellow, and Green Rules (Example)
Green: standard or deviation ≤10%
Huang: The deviation is 10%~20%, and we will follow up in the stand-up meeting on the same day.
Red: deviation from target >20%, upgrade immediately
The signboard must be hung in a visible location in the war room, and "only reading the monthly report" is prohibited.
Practical training on quality management during the ramp-up period of new production lines

## Slide 23
Knowledge accumulation: Problems → Countermeasures → Standardization
① Problem record: phenomenon/time/equipment/batch/preliminary judgment
② Countermeasure verification: temporary + long-term, tracking effect
③ Standardization: Update CP/SOS/PFMEA and provide training within 72 hours
Practical training on quality management during the ramp-up period of new production lines

## Slide 24
Precipitated rewards: The ramp-up cycle can be "learned"
The problems encountered in the climbing stage will most likely be encountered again in the mature stage.
Case: A company that built a factory three times - 8 months for the first time → 3 months for the third time
Reason for shortening: It’s not that the equipment is better, but that the first two knowledge can be directly called
The closing report itself is the "starting asset" for the next new line.
Practical training on quality management during the ramp-up period of new production lines

## Slide 25
05
Traps and exit from mass production
Stabilize first, then speed up; close the case after meeting the standards

## Slide 26
Trap 1: Taking output as the only priority
wrong philosophy
Ship first, rectify later Produced with problems → higher repair/scrap/claim costs The climb is lengthened instead
correct philosophy
The speed at which quality meets standards determines the speed at which output meets standards. Quality provides "the conditions for the production line to run" When accepting concessions, you must clearly answer: risks / additional controls / recovery conditions
Practical training on quality management during the ramp-up period of new production lines

## Slide 27
Trap 2: Relaxing inspection intensity too early
Tightening in the initial stage (full inspection/increased frequency/extended first article window) → After a few weeks of stability, the management urged "cost reduction"
Resume random inspections under false stability → Batch missed inspections are common
Downgrade rule: "Continuous stable double cycle"
Example: The plan will be tightened for 4 weeks → all indicators must be passed for 8 consecutive weeks before it can be downgraded
Practical training on quality management during the ramp-up period of new production lines

## Slide 28
Trap 3: Change is the biggest enemy during the ramp-up period
Modify while crawling: new model/process optimization/material change → the variables are disturbed again, and all the previous efforts in convergence are wasted.
Implement "change freeze": no major quality/security risks, no unnecessary changes introduced
Necessary changes: special war room review + impact assessment + additional verification + buffer zone
Change is not a ban, but "planned, verified, and buffered"
Practical training on quality management during the ramp-up period of new production lines

## Slide 29
Six criteria for exiting mass production (the case will be closed only when all are met)
# | Exit conditions
1 | All CTQ: Cpk≥1.33, and there is no abnormal trend in four consecutive groups of samples
2 | Daily pass rate for 30 consecutive working days ≥ established target
3 | OEE ≥ design 85%, equipment shutdown ≤ mature line benchmark
4 | 100% of key positions ≥L2, and ≥30% reach L3
5 | Qualification rate of supplier's incoming materials for 3 consecutive months ≥ mature acceptance standard
6 | Significant issues standardized output; PFMEA/CP/SOS updated
Practical training on quality management during the ramp-up period of new production lines

## Slide 30
Case closure and temporary mechanism exit
The war room issues a ramp-up closing report → Management review and confirmation → Officially transferred to the mass production system
Strict inspection / rapid upgrade / war room: phase out according to the predetermined plan
The closing report must include: parameter convergence trajectory, main problems and countermeasures, experience and lessons learned
Next sentence When New Line starts, the first must-read material is this closing report.
Practical training on quality management during the ramp-up period of new production lines

## Slide 31
06
workshop
Draft a list of milestones and stand-up meetings for the factory

## Slide 32
Practice in groups (30-40 minutes)
① Select a production line that is about to/is climbing (or a historical desensitization case)
② Write down the M1~M4 quality status milestones (indicators + continuous stability conditions)
③ List the three-column template for the daily stand-up meeting in the war room: yesterday’s indicators / today’s risks / upgrade matters
④ Pick a CTQ and draw a mini "parameter-quality matrix" (≥3 CPP)
⑤ 5-minute report for each group: Which of the four dimensions is the greatest risk?
Practical training on quality management during the ramp-up period of new production lines

## Slide 33
Implementation Checklist 2 weeks after class
Publish the ramp-up plan (including promotion/demotion rules) and put it on the wall
Appoint core members of the war room and fix daily stand-up time
Online daily/weekly dashboard and red, yellow and green rules
Establish ramp tracking cards for key equipment; initiate L1/L2/L3 certification for key positions
Issue "Special Delivery Requirements During the Ramp-Up Period" letter to key suppliers
Practical training on quality management during the ramp-up period of new production lines

## Slide 34
End in one sentence
The new line ramp is a strategic window period for quality - managing it well is equal to winning stability in the next three years.
The status of the project determines "whether it can be done"; the climb determines "whether it is stable".
The plan manages the status, the upgrade manages the speed, the war room manages the coordination, and the precipitation manages the next time.
Practical training on quality management during the ramp-up period of new production lines

## Slide 35
Q & A
Supporting think tank article id=186 qtank.org/article?id=186 Knowledge No. 15.2.1 · New factory/new production line ramp-up

## Slide 36
thanks for listening
qtank.org
QTank
qtank.org