## Slide 1
Project Quality Gates
Concept · Practical Operation · Advanced · Series of Integrated Training
Stage-Gate structured decisions · From checkbox reviews to measurable control · Knowledge Code 4.4.1
QTank
Knowledge number 4.4.1 · Project quality gate (Gate)
qtank.org

## Slide 2
Training Objectives
Supporting article id=194 / 196 / 187 · It is recommended to train within 3 to 4 hours
Establish the concept of quality gate: no jumps in stages, data-based decision-making, separation of powers and responsibilities
Distinguish three types of gates: stage gates/deliverable gates/risk trigger gates, master Gate0～5
Run through the six-step closed loop: planning → preparation → meeting → decision-making → rectification → closing
Avoid the seven major misunderstandings and use the requirements/design checklist to make quantitative and accurate decisions
Connect with APQP, agile/lean adaptation and digital evolution, and be able to draft implementation paths
Practical training on project quality gate (series integration)

## Slide 3
Comparison of course map and series of articles
module | theme | article
01 | Origin, Concept, Type and Gate0~5 | (1) 194 Conceptual Framework
02 | Six-step process, roles, and five essentials | (2) 196 Practical Guide
03 | Checklist, Seven Misunderstandings | (2) 196 Practical Guide
04 | APQP integration, agile and lean, digitalization | (3) 187 advanced path
05 | Cross-industry comparison + implementation path + workshop | (3) 187 + comprehensive
Practical training on project quality gate (series integration)

## Slide 4
01
Conceptual framework
Origin · Three major concepts · Three types of gates · Gate0～5

## Slide 5
Origin: From "Stage Disconnect" to Stage-Gate
Pain points in the automobile industry in the 1980s: Design was thought to be complete, but manufacturing felt there was not enough input → Mass production broke out intensively
Prototype of countermeasures: Set up formal checkpoints at stage transitions, and those who fail to meet the exit criteria are not allowed to enter the next stage.
Cooper Stage-Gate: Stage + Go/Kill gate → reusable methodology (pharmaceutical/chemical/fast-moving consumer goods...)
Standard upgrade: ISO 9001:2015 §8.3; IATF/APQP; PMBOK Phase Gate; CMMI review practice
The core logic remains unchanged: structured stage decision-making, replacing fuzzy subjective judgments, and intercepting problems before they become amplified.
Practical training on project quality gate (series integration)

## Slide 6
Three core concepts
① Stages cannot be jumped: concept/design/verification each have unique value; skipping a stage = using the cost of the next stage to make up for the defects in the stage
② Decision-making requires data: "Looks good" is prohibited; exit conditions can be tested (DFMEA coverage, Cpk, use case pass rate)
③ Rights and responsibilities must be separated: the executor has progress pressure; the independent Gate Keeper has the right to review and make decisions
Practical training on project quality gate (series integration)

## Slide 7
Four core values
value | Main points
risk front | Error correction cost during the design period ≈ 1/10 after mass production; multi-channel protective nets are screened out at the stage
Cross-functional collaboration | Research/engineering/purchasing/manufacturing/quality confront each other; break down departmental barriers
Decisions are traceable | Review report + problem list + responsible person; audit basis and experience samples
Resource matching risk | Strict gate control for high risks; simplified channels for low risks to avoid one size fits all
Practical training on project quality gate (series integration)

## Slide 8
Three types: backbone + supplementary network
Phase quality gate: Phase transition confirmation completeness and next phase start conditions (deliverables/risks/budget/customer requirements)
Deliverables quality gate: special review of key outputs (requirement specifications, three-dimensional digital model freezing...), with finer granularity
Risk trigger gate: Automatic triggering of preset signals (supplier delay, substandard indicators, major changes) - event driven
Practice combination: Stage gate serves as the skeleton, and deliverable gate + risk gate serve as supplement, covering the entire life cycle
Practical training on project quality gate (series integration)

## Slide 9
Typical settings: Gate 0～Gate 5
Door | name | The key to quality is accurate (abstract)
G0 | Project start | Charter/Team/Preliminary Plan; Quality Objectives and Quality Planning Framework
G1 | concept approval | Feasibility; preliminary list of special features; first draft of DFMEA
G2 | Plan freeze | Program review; DFMEA update; DVP approval; supplier preliminary selection
G3 | Preparation for trial production | DV passed; PFMEA/CP first version; tooling in place
G4 | Mass production release | PV/PPAP; Cpk; mass production CP/SOS; training completed
G5 | Project closed | Early containment; documentation; lessons learned; quality summary
Practical training on project quality gate (series integration)

## Slide 10
Set the Three Principles + Change Gate
The number of door points is moderate: 3 to 7 for typical product development; they are located at the decisive nodes for success or failure, and not every detail is delivered.
Standards are clear and measurable: prohibit “basically completed”; use quantitative inspection items to reduce disputes
Separation of reviewers and executors: project team presentation; door owner/committee decision-making
Optional Change Gate: Design/process changes after mass production are subject to the same strict review
Practical training on project quality gate (series integration)

## Slide 11
Connection with standard system
System | Integration Point
ISO 9001 §8.3 | Design and development review/verification/validation → Door-to-door records are evidence of compliance
IATF 16949 / APQP | Five-stage quality gate for automotive suppliers; audit and re-inspection gate records
PMBOK | Phase Gate / Steering Committee Go-Adjustment-Termination
CMMI | Peer review and stage review; door maturity reflects organizational process capabilities
Practical training on project quality gate (series integration)

## Slide 12
02
Practical process
Six-step closed loop · Five essentials · Three roles

## Slide 13
Six-step closed loop overview
①Plan
②Prepare materials
③Review meeting
④Decision making
⑤Following and rectification
⑥Close review
Practical training on project quality gate (series integration)

## Slide 14
①Plan · ②Prepare
Develop a quality gate plan
The start-up period is clear: number and location of doors Admission standards, committees, timelines Document Checklist and Decision Rules Written into PQP and approved by Management Committee Become a key indicator of progress dashboard
Prepare review package
Deliverables list + self-inspection report Quality Metrics/Risk/Issue Change Log Key outputs: Admission self-inspection checklist You can apply only if you meet all the required options Proactively digest known issues and don’t leave them to meetings
Practical training on project quality gate (series integration)

## Slide 15
③Three-stage review meeting
Reporting: Project managers present progress, deliverables and self-inspection results
Questioning: sampling review by committee members and independent verification of self-inspection conclusions
Decision-making: Conclusion after closed-door discussion
The atmosphere is about things, not people; the goal is to discover problems and promote improvements
Usually ≤2 hours; overtime indicates insufficient preparation or the topic is out of bounds → Post-meeting topic
Record each opinion and responsible person as a basis for tracking
Practical training on project quality gate (series integration)

## Slide 16
④Four types of decision results
decision making | meaning | Follow-up
Go pass | Fully compliant with access | Enter the next stage
Conditional Go | Basically consistent, with a few non-critical items | Time-limited rectification; door-to-door verification
Rework | more serious problem | Review after rectification; minimal cost
No Go failed | Major flaws/risks | Pause until resolved; stop loss promptly
Practical training on project quality gate (series integration)

## Slide 17
⑤Correction tracking · ⑥Close and review
Rectification items: sole responsible person + deadline + verification standard; quality assurance verification closed
Closed loop: discovery → correction → verification → closure, recorded in weekly report and risk log; upgraded after expiry
After all are closed: the door owner signs the closure confirmation → Only then can the next stage of substantive work begin
Process review: Should standards be adjusted? How efficient is it? Feedback into follow-up door plan
Practical training on project quality gate (series integration)

## Slide 18
Five operational essentials
Standards first: Compilation of checklists at startup; accurate quantification (e.g. RPN>100 has completed ≥3 improvements)
Decision-making level: G0/G1 project manager; G2/G4 cross-functional committee; mass production door production manager one-vote veto
Independent review: quality is the gatekeeper and is not responsible for progress; committee certification and rotation
Exception management: conditional release/Deviation higher-level batch/No-Go; written inclusion in tracking
Closed-loop tracking: non-compliance with the entry system; review the last rectification first; build a problem database for pattern recognition
Practical training on project quality gate (series integration)

## Slide 19
Key roles and responsibilities
Role | Key points of responsibilities
Gate Keeper | Final closing authority; reports to senior quality committee; does not report to project manager
project manager | Applicant: materials, conference affairs, reporting, implementation of rectification, and responsibility for results
Jury | Cross-functional expert confrontation; relatively stable accumulation of experience + regular rotation to prevent fatigue
Practical training on project quality gate (series integration)

## Slide 20
03
Tools and pit avoidance
Checklist Template · Seven Misunderstandings

## Slide 21
Requirements Quality Gate Checklist (Example Summary)
# | Check items
1 | Requirements document fully covers business needs
2 | Each requirement has a unique identifier
3 | Each requirement has clear acceptance criteria
4 | Requirements-goal traceability matrix
5 | Key requirements have been confirmed with customers/users
6 | Impact analysis and approval of changes completed
7 | Demand risks have been entered into the risk register
8 | Requirements document passes peer review
Practical training on project quality gate (series integration)

## Slide 22
Demand gate determination rules (example)
All "Yes" → Go
1~2 items are "No" and not critical → Conditional Go + corrective plan
≥3 "No" or 1 key "No" → Rework, review after rectification
Compile a complete department point check list during the startup period, which can be dynamically fine-tuned during execution
Practical training on project quality gate (series integration)

## Slide 23
Design Quality Gate Checklist (Example Summary)
# | Check items
1 | The solution meets all functional requirements
2 | Analysis of advantages and disadvantages of technology selection completed
3 | The interface is clearly defined and confirmed by relevant parties
4 | Key design constraints are fully identified
5 | The plan passed peer technical review
6 | DFMEA covers all severity levels ≥9
7 | There are alternatives to the highest risk option
8 | Design verification plan aligned with customer
Practical training on project quality gate (series integration)

## Slide 24
Seven major misunderstandings and solutions (1/2)
① Going through the motions: independent door owner + high-level support No Go; compliance audit; accountability for violations
② Ambiguous standards: split into verifiable inspection items (severity ≥ 9, control measure verification completion rate 100%)
③ The checklist is too heavy: a differentiated list based on risks; daily meetings are preceded; door meetings only confirm key items
④ Too many gate points: return to the essence, generally 5 to 7 projects correspond to major milestones
Practical training on project quality gate (series integration)

## Slide 25
Seven major misunderstandings and solutions (2/2)
⑤ Emphasis on door control but not on process: Break down the door requirements into weekly meetings/design reviews, and the front door will be basically mature.
⑥ Lack of timely feedback: 24h initial report, 48h formal report; early warning of question bank classification
⑦ Ignoring knowledge accumulation: building a gated experience database and identifying typical unqualified items/root causes/countermeasures patterns
Practical training on project quality gate (series integration)

## Slide 26
04
Advanced Fusion
APQP · Agile and Lean · Digitalization

## Slide 27
APQP Five Stages ↔ Quality Gate (example comparison)
APQP stage | Corresponding door | Typical exit (summary)
Planning and Definition | G1 start | Project proposal; feasibility ≥90%
Product design and development | G2 design | DFMEA 100%; design verification passed
process design development | G3 process | PFMEA RPN reduction; equipment acceptance
Product process confirmation | G4 mass production | Cpk≥1.33；GR&R≤10%；PSW
feedback assessment correction | G5 improvements | Batch defective ≤ target; customer satisfaction
Practical training on project quality gate (series integration)

## Slide 28
Case: Global auto parts company
Setting G0~G5: concept door intervention earlier; G1~G4 for APQP; G5 review after mass production
Effect: Development cycle 36→24 months; design change ↓40%; 3-month zero-kilometer defect rate 95.2%→98.7%
Enlightenment: Gates and milestones are combined on the dashboard, and progress uses "gate passing status" as the key indicator
Migrant: Stage-gate logic (such as ISO 13485 review node) is also available for aviation/medical equipment/electronics, etc.
Practical training on project quality gate (series integration)

## Slide 29
Adaptation in Agile/Lean environments
agile
Stage Gate → Incremental Release Control Iterative lightweight gate: acceptance/coverage/defects/technical debt SAFe: PI formal system gate CI/CD automatic gating: non-compliance blocks merge/release Review from "days" to "minutes"
Lean
knowledge-based decision-making Knowledge template/A3 presents decision-making information Gate reviewers ask: Is the information sufficient to make informed decisions? Upgraded from administrative approval to knowledge management node The principle remains unchanged: reach the maturity level before entering the next stage.
Practical training on project quality gate (series integration)

## Slide 30
Digital four-dimensional evolution
① Automatic collection: capture Cpk, pass rate, delivery completion from PLM/MES/QMS - say goodbye to self-evaluation and reporting
② Multi-level billboard: company/project/department; red warning automatic notification to prevent information transmission delay
③ Risk prediction: Historical door data identifies easy-to-fail door points/project types/easy-to-neglect standards
④ Cross-system linkage: PLM release→delivery door; procurement anomaly→risk door; CI substandard→block release
Practical training on project quality gate (series integration)

## Slide 31
Case: Domestic automotive electronic digital door
7 paper nodes → online automated door points
Stage conversion 15→6 working days; preparation 3 days→half a day; pass rate 92%→97% (more accurate data, stricter execution)
New model project: Discover mold delays in advance → Alternatives → Avoid entire project delays
Practical training on project quality gate (series integration)

## Slide 32
05
landing path
Cross-industry comparison · Four stages and five steps · Workshop

## Slide 33
Cross-industry practice comparison (summary)
Dimensions | manufacture | software | architecture | pharmaceutical
Gate points | 3～5 | 4～6(+iteration) | 5～8 | 6～10(Regulations)
typical path | Concept→mass production | Requirement→Release | Feasibility study → completion | R&D→Production
Admission example | Cpk/sample | Coverage/Defects | Drawings/Processes | Clinical/Registration
decision making | majority vote | PM+Technical Committee | Supervision sign | regulatory approval
Practical training on project quality gate (series integration)

## Slide 34
four strategic stages
① Pilot 3 to 6 months: 1 to 2 high-risk projects; 3 to 4 key gates; rapid iteration template
② System solidification 2 to 3 months: standards/checklists/responsibilities are incorporated into system documents; training and implementation
③ Comprehensive promotion: new products + major changes; low-risk Fast Track; building review database
④ Continuous optimization: pass rate/failure distribution/cycle; associated on-time delivery, customer complaints, and rework costs
Practical training on project quality gate (series integration)

## Slide 35
Five implementation steps
①Identify key nodes
②Quantitative access and exit
③Independent review team
④Tools/IT platform
⑤Continuous improvement mechanism
Practical training on project quality gate (series integration)

## Slide 36
Case: Two-year iteration of medium-sized equipment manufacturing
Initially set to 8 doors → merged into 5 (overload) half a year later
Adjust the threshold according to data: Cpk 1.67→1.33 (matching the real accuracy requirements)
Two years later: on-time delivery 68%→89%; quality complaints ↓52%
Lesson: Quality gate is a learning system, not a one-time system document
Practical training on project quality gate (series integration)

## Slide 37
Workshop (30-40 minutes)
① Select an ongoing/historical project and draw the names of 5 to 7 suggested door points
② Write 8 quantitative inspection items for one of the key gates (such as plan freezing or mass production release)
③ Designate the source department of the door owner and the functional composition of the committee
④ List the 2 misunderstandings that the organization is most likely to fall into and their countermeasures
⑤ 5-minute report for each group: Who should be chosen for the first pilot project? Why?
Practical training on project quality gate (series integration)

## Slide 38
Implementation checklist for two weeks after class
Draft a "Quality Gate Plan" template and link it to a pilot project
Complete the first version of the requirements gate + design gate (or mass production gate) checklist
Clear gate owner appointment and No Go upgrade path in writing
Add two columns "gate status/rectification overdue" to the weekly report
Read the supporting articles 194→196→187, and add our factory cases to the experience database
Practical training on project quality gate (series integration)

## Slide 39
End in one sentence
The quality gate is not to set up barriers, but to ensure adequate preparation before making every decision.
Concepts govern direction, processes govern closed loops, checklists govern objectivity, and digitization governs speed.
The value is not in the level itself, but in the improvement of organizational capabilities driven by systematic decision-making.
Practical training on project quality gate (series integration)

## Slide 40
Q & A
Supporting series of articles (1) Concept id=194 · (2) Practical operation id=196 · (3) Advanced id=187 qtank.org · Knowledge No. 4.4.1

## Slide 41
thanks for listening
qtank.org
QTank
qtank.org